## Slide 1: True North Scorecard FY 19/20 & FY 20/21 Hoshin Roadmap
Notes: Developing an environment that gets staff aligned and

## Slide 5
2019
Today
Jul
Aug
Sep
Oct
Nov
Dec
Jan
Feb
Mar
Nov 7
Dec 20
6 days
Study/Adjust from previous deployment
17 days
24 days
16 days
25 days
FY 20-21 ZSFG Hoshin Roadmap
Expected Hoshin for FY 20/21 - POSTPONED
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
2020
COVID-19
Hoshin Progress Interrupted
Hoshin Roadmap Approved
X-Matrix Outcome Targets Finalized
Key Performance Indicators Finalized
Strategies Updated & Deployed
Plan for next Hoshin cycle
Do (Deploy) updated strategies
FY 19/20 Strategies Deployed
Weekly Reporting Of KPIs Begins
Summary of FY 19/20:
Varying levels of deployment achieved throughout organization
KPIs were established parallel to deployment
  Created gaps in measuring and alignment to Strategic A3s
  COVID interrupted our reporting process and prevented us from having a Hoshin event in May 2020 to reflect and adjust
Adjustments for FY 20/21:
“Flow” of Hoshin
  Adjusting strategies & metrics through weekly meetings
  Deployment will happen continuous over time through end of calendar year 2020 as the True North Scorecard is finalized